## Executive Summary
🔁 PLM Data Migration & Testing — Executive Summary Report
Generated: 06 April 2026, 10:04 ¦ Project: Generic PLM → Target PLM ¦ Prepared by: Sia Sharma
Total Records | Parts | BOM Entries | Documents | ECOs | Issues Found | Test Cases | Pass Rate
530 | 200 | 150 | 100 | 80 | 18 | 31 | 100%
MIGRATION STATUS BY ENTITY
Entity | Total | Completed | Pending | In Progress | Failed | Completion %
Parts | 200 | 87 | 51 | 45 | 17 | 43.5%
BOM | 150 | 86 | 41 | 0 | 23 | 57.33%
Documents | 100 | 52 | 35 | 0 | 13 | 52%
ECO | 80 | 48 | 22 | 0 | 10 | 60%
VALIDATION ISSUES SUMMARY
Entity | Issue Type | Count | Severity | Action Required
BOM | Invalid Value | 1 | High | Review & resolve
BOM | Null Value | 1 | High | Review & resolve
BOM | Orphan Record | 1 | High | Review & resolve
Documents | Null Value | 1 | High | Review & resolve
Documents | Orphan Record | 1 | High | Review & resolve
ECO | Business Rule Violation | 6 | Critical | Fix before migration
ECO | Invalid Reference | 1 | High | Review & resolve
ECO | Null Value | 1 | High | Review & resolve
Parts | Invalid Reference | 1 | High | Review & resolve
Parts | Invalid Value | 1 | High | Review & resolve
Parts | Null Value | 2 | High | Review & resolve
Parts | Null Value | 1 | Medium | Monitor

## Validation Issues Log
PLM Migration — Validation Issues Log
Entity | Record_ID | Field | Issue_Type | Severity | Detail | Detected_At
Parts | PT-00006 | Part_Name | Null Value | High | Part name is missing | 2026-04-06 10:03:23
Parts | PT-00013 | Unit_Cost_INR | Invalid Value | High | Negative cost: -999.0 | 2026-04-06 10:03:23
Parts | PT-00026 | Revision | Null Value | High | Revision is missing | 2026-04-06 10:03:23
Parts | PT-00041 | Status | Invalid Reference | High | Unknown status: INVALID_STATUS | 2026-04-06 10:03:23
Parts | PT-00061 | Weight_KG | Null Value | Medium | Weight is missing | 2026-04-06 10:03:23
BOM | BOM-00004 | Quantity | Invalid Value | High | Quantity must be > 0, found: 0 | 2026-04-06 10:03:23
BOM | BOM-00011 | Parent_Part_ID | Null Value | High | Parent Part ID missing | 2026-04-06 10:03:23
BOM | BOM-00023 | Child_Part_ID | Orphan Record | High | Child not in Parts: PT-99999 | 2026-04-06 10:03:23
Documents | DOC-00008 | Doc_Name | Null Value | High | Document name is missing | 2026-04-06 10:03:23
Documents | DOC-00016 | Related_Part_ID | Orphan Record | High | Part not found: PT-00000 | 2026-04-06 10:03:23
ECO | ECO-00005 | Priority | Null Value | High | Priority is missing | 2026-04-06 10:03:23
ECO | ECO-00007 | Approved_By | Business Rule Violation | Critical | Approved ECO has no approver | 2026-04-06 10:03:23
ECO | ECO-00008 | Approved_By | Business Rule Violation | Critical | Approved ECO has no approver | 2026-04-06 10:03:23
ECO | ECO-00013 | Approved_By | Business Rule Violation | Critical | Approved ECO has no approver | 2026-04-06 10:03:23
ECO | ECO-00019 | Status | Invalid Reference | High | Unknown status: UNKNOWN | 2026-04-06 10:03:23
ECO | ECO-00036 | Approved_By | Business Rule Violation | Critical | Approved ECO has no approver | 2026-04-06 10:03:23
ECO | ECO-00045 | Approved_By | Business Rule Violation | Critical | Approved ECO has no approver | 2026-04-06 10:03:23
ECO | ECO-00059 | Approved_By | Business Rule Violation | Critical | Approved ECO has no approver | 2026-04-06 10:03:23

## Test Case Results
PLM Migration — Test Case Execution Report
Test_Case_ID | Test_Name | Entity | Category | Description | Expected_Result | Actual_Result | Status | Severity | Remarks
TC-001 | Parts Record Count | Parts | Extraction | Verify 200 parts extracted | 200 | 200 | PASS | High
TC-002 | BOM Record Count | BOM | Extraction | Verify 150 BOM records | 150 | 150 | PASS | High
TC-003 | Document Record Count | Docs | Extraction | Verify 100 documents | 100 | 100 | PASS | High
TC-004 | ECO Record Count | ECO | Extraction | Verify 80 ECOs | 80 | 80 | PASS | High
TC-005 | Parts Column Count | Parts | Extraction | Verify 13 columns in Parts | 13 | 13 | PASS | Medium
TC-006 | BOM Column Count | BOM | Extraction | Verify 9 columns in BOM | 9 | 9 | PASS | Medium
TC-007 | Source System Tag - Parts | Parts | Extraction | All rows tagged with source | True | True | PASS | Medium
TC-008 | Source System Tag - BOM | BOM | Extraction | All rows tagged with source | True | True | PASS | Medium
TC-009 | Parts - Unique IDs | Parts | Data Integrity | No duplicate Part_IDs | 0 | 0 | PASS | Critical
TC-010 | BOM - Unique IDs | BOM | Data Integrity | No duplicate BOM_IDs | 0 | 0 | PASS | Critical
TC-011 | Docs - Unique IDs | Docs | Data Integrity | No duplicate Doc_IDs | 0 | 0 | PASS | Critical
TC-012 | ECO - Unique IDs | ECO | Data Integrity | No duplicate ECO_IDs | 0 | 0 | PASS | Critical
TC-013 | Parts - No Null Part_ID | Parts | Data Integrity | Part_ID column has no nulls | 0 | 0 | PASS | Critical
TC-014 | BOM - No Null BOM_ID | BOM | Data Integrity | BOM_ID column has no nulls | 0 | 0 | PASS | Critical
TC-015 | Parts - Null Part Names | Parts | Validation | Detect null Part Names | True | True | PASS | High | 1 null(s) found
TC-016 | Parts - Negative Cost | Parts | Validation | Detect negative unit costs | True | True | PASS | High | 1 negative cost(s)
TC-017 | Parts - Invalid Status | Parts | Validation | Detect invalid status values | True | True | PASS | High | 1 invalid status(es)
TC-018 | BOM - Orphan Children | BOM | Validation | Detect orphan BOM child refs | True | True | PASS | Critical | 1 orphan(s)
TC-019 | BOM - Zero Quantity | BOM | Validation | Detect zero/negative quantity | True | True | PASS | Medium | 1 zero-qty row(s)
TC-020 | Docs - Orphan Part Refs | Docs | Validation | Detect doc→part orphan refs | True | True | PASS | High | 1 orphan(s)
TC-021 | ECO - Invalid Status | ECO | Validation | Detect invalid ECO statuses | True | True | PASS | High | 1 invalid(s)
TC-022 | ECO - Null Priority | ECO | Validation | Detect missing ECO priorities | True | True | PASS | Medium | 1 null(s)
TC-023 | ECO - Approved No Approver | ECO | Validation | Approved ECO must have approver | True | True | PASS | Critical | 6 violation(s)
TC-024 | Migration Status - Parts Completed | Parts | Migration QA | At least 30% parts migrated | True | True | PASS | High | 43.5% completed
TC-025 | Migration Status - BOM Completed | BOM | Migration QA | At least 50% BOM migrated | True | True | PASS | High | 57.3% completed
TC-026 | Total Issues Detected | All | Migration QA | Validation engine detects all issues | True | True | PASS | High | 18 total issues logged
TC-027 | Issue Severity Breakdown | All | Migration QA | Critical issues exist in log | True | True | PASS | Critical
TC-028 | Parts Schema Intact | Parts | Regression | Required columns present | True | True | PASS | High
TC-029 | BOM Schema Intact | BOM | Regression | Required columns present | True | True | PASS | High
TC-030 | Docs Schema Intact | Docs | Regression | Required columns present | True | True | PASS | High
TC-031 | ECO Schema Intact | ECO | Regression | Required columns present | True | True | PASS | High
TOTAL: 31 Tests ¦ PASSED: 31 ¦ FAILED: 0 | [6 empty] | 100.0%

## Source Data Preview
Source Data Preview — Parts (first 30 rows)
Part_ID | Part_Name | Category | Revision | Status | UOM | Weight_KG | Unit_Cost_INR | Owner | Created_Date | Modified_Date | Source_System | Migration_Status
PT-00001 | Gear A 859 | Electrical | D | Draft | M | 4.1 | 12931.49 | Amit Shah | 2023-10-18 | 2024-10-04 | Legacy_PLM_v1 | Pending
PT-00002 | Bracket B 328 | Assembly | C | Draft | M | 4.115 | 7010.84 | Vikram Iyer | 2024-06-11 | 2023-09-06 | Legacy_PLM_v1 | Completed
PT-00003 | Sensor Y 204 | Software | A | Released | KG | 20.366 | 41754.77 | Priya Nair | 2024-11-10 | 2023-04-15 | Legacy_PLM_v1 | In Progress
PT-00004 | Filter A 704 | Software | D | Released | L | 16.633 | 49220.89 | Priya Nair | 2024-10-10 | 2024-12-14 | Legacy_PLM_v1 | In Progress
PT-00005 | Relay A 130 | Mechanical | D | Released | EA | 13.081 | 26308.22 | Vikram Iyer | 2024-09-26 | 2023-11-05 | Legacy_PLM_v1 | Failed
PT-00006 |  | Mechanical | C | Released | EA | 8.977 | 8625.38 | Sneha Patil | 2023-12-10 | 2024-12-01 | Legacy_PLM_v1 | Pending
PT-00007 | Filter X 127 | Mechanical | A | Released | L | 21.931 | 13651.75 | Vikram Iyer | 2023-04-06 | 2024-09-06 | Legacy_PLM_v1 | Completed
PT-00008 | Filter B 833 | Firmware | C | In Review | KG | 9.817 | 968.61 | Sneha Patil | 2023-08-29 | 2023-05-04 | Legacy_PLM_v1 | Completed
PT-00009 | Filter D 325 | Software | A | Released | M | 20.417 | 45719.23 | Vikram Iyer | 2024-11-19 | 2024-08-02 | Legacy_PLM_v1 | Pending
PT-00010 | Switch X 384 | Software | E | Released | EA | 10.984 | 5931.67 | Vikram Iyer | 2023-11-14 | 2023-02-12 | Legacy_PLM_v1 | Completed
PT-00011 | Bolt B 814 | Mechanical | B | Obsolete | SET | 9.43 | 28847 | Raj Mehta | 2023-08-19 | 2023-12-22 | Legacy_PLM_v1 | Failed
PT-00012 | Relay C 384 | Assembly | B | Released | SET | 11.572 | 13739.06 | Priya Nair | 2023-07-23 | 2024-06-29 | Legacy_PLM_v1 | Pending
PT-00013 | Sensor B 881 | Firmware | B | Obsolete | L | 7.541 | -999 | Vikram Iyer | 2023-05-31 | 2024-03-14 | Legacy_PLM_v1 | Completed
PT-00014 | Cable A 194 | Mechanical | C | Released | KG | 18.693 | 32588.45 | Vikram Iyer | 2023-01-26 | 2024-11-08 | Legacy_PLM_v1 | Completed
PT-00015 | Relay A 467 | Mechanical | E | Released | EA | 12.573 | 41495.6 | Amit Shah | 2023-02-17 | 2024-01-15 | Legacy_PLM_v1 | Completed
PT-00016 | Cable X 370 | Mechanical | A | In Review | KG | 5.813 | 10360.74 | Priya Nair | 2023-09-08 | 2023-03-12 | Legacy_PLM_v1 | Completed
PT-00017 | Bolt Y 570 | Electrical | D | In Review | EA | 22.49 | 599.24 | Amit Shah | 2024-05-01 | 2024-06-02 | Legacy_PLM_v1 | Pending
PT-00018 | Filter A 487 | Electrical | A | Obsolete | L | 9.603 | 6887.44 | Priya Nair | 2024-09-17 | 2024-10-25 | Legacy_PLM_v1 | Failed
PT-00019 | Gear X 400 | Electrical | D | In Review | L | 13.593 | 45005.93 | Amit Shah | 2023-03-16 | 2023-12-16 | Legacy_PLM_v1 | Failed
PT-00020 | Valve C 691 | Mechanical | A | Obsolete | SET | 22.663 | 43700.81 | Vikram Iyer | 2024-04-11 | 2023-01-13 | Legacy_PLM_v1 | Completed
PT-00021 | Module Y 171 | Software | E | Released | KG | 15.61 | 29890.78 | Vikram Iyer | 2024-02-29 | 2024-03-06 | Legacy_PLM_v1 | Completed
PT-00022 | Bolt Y 333 | Mechanical | D | Released | SET | 2.931 | 30045.82 | Raj Mehta | 2024-10-06 | 2024-05-16 | Legacy_PLM_v1 | Completed
PT-00023 | Bracket A 975 | Mechanical | C | Obsolete | KG | 23.496 | 33268.58 | Amit Shah | 2024-08-12 | 2023-04-19 | Legacy_PLM_v1 | In Progress
PT-00024 | Module A 489 | Electrical | A | Obsolete | SET | 15.696 | 8809.8 | Sneha Patil | 2023-07-19 | 2024-03-19 | Legacy_PLM_v1 | Completed
PT-00025 | Bracket D 750 | Electrical | A | Draft | M | 8.379 | 45724.88 | Raj Mehta | 2024-12-14 | 2024-01-06 | Legacy_PLM_v1 | Completed
PT-00026 | Cable B 479 | Firmware |  | Released | M | 3.49 | 20967.59 | Amit Shah | 2024-01-29 | 2024-10-12 | Legacy_PLM_v1 | Completed
PT-00027 | Cable B 786 | Mechanical | C | Released | M | 19.853 | 19187.77 | Amit Shah | 2024-05-21 | 2024-04-15 | Legacy_PLM_v1 | Completed
PT-00028 | Bracket Y 799 | Electrical | C | Obsolete | M | 15.506 | 25969.94 | Raj Mehta | 2024-02-14 | 2024-12-25 | Legacy_PLM_v1 | In Progress
PT-00029 | Gear X 750 | Software | E | Released | EA | 13.341 | 2395.95 | Vikram Iyer | 2023-09-07 | 2023-06-06 | Legacy_PLM_v1 | Pending
PT-00030 | Sensor X 846 | Mechanical | C | Draft | M | 22.348 | 8355.85 | Amit Shah | 2023-06-01 | 2024-03-21 | Legacy_PLM_v1 | Pending

## SQL Scripts Reference
SQL Validation & Migration Scripts Reference
Script Name | Purpose | SQL Query
EXTR-001 | Count total parts extracted | SELECT COUNT(*) AS total_parts FROM source_parts;
EXTR-002 | Count total BOM records | SELECT COUNT(*) AS total_bom FROM source_bom;
EXTR-003 | Verify source system tag | SELECT COUNT(*) FROM source_parts WHERE Source_System <> 'Legacy_PLM_v1';
VAL-001 | Find null Part Names | SELECT Part_ID FROM source_parts WHERE Part_Name IS NULL;
VAL-002 | Find negative unit costs | SELECT Part_ID, Unit_Cost_INR FROM source_parts WHERE Unit_Cost_INR < 0;
VAL-003 | Find invalid part statuses | SELECT Part_ID, Status FROM source_parts WHERE Status NOT IN ('Released','In Review','Obsolete','Draft');
VAL-004 | Find orphan BOM child references | SELECT b.BOM_ID, b.Child_Part_ID FROM source_bom b LEFT JOIN source_parts p ON b.Child_Part_ID = p.Part_ID WHERE p.Part_ID IS NULL;
VAL-005 | Find zero or null BOM quantities | SELECT BOM_ID, Quantity FROM source_bom WHERE Quantity IS NULL OR Quantity <= 0;
VAL-006 | Find orphan document references | SELECT d.Doc_ID, d.Related_Part_ID FROM source_documents d LEFT JOIN source_parts p ON d.Related_Part_ID = p.Part_ID WHERE p.Part_ID IS NULL;
VAL-007 | Find Approved ECOs without approver | SELECT ECO_ID FROM source_eco WHERE Status = 'Approved' AND Approved_By IS NULL;
VAL-008 | Find invalid ECO statuses | SELECT ECO_ID, Status FROM source_eco WHERE Status NOT IN ('Open','In Review','Approved','Rejected','Closed');
MIG-001 | Migration completion rate by entity | SELECT 'Parts' AS Entity, Migration_Status, COUNT(*) AS Count FROM source_parts GROUP BY Migration_Status UNION ALL SELECT 'BOM', Migration_Status, COUNT(*) FROM source_bom GROUP BY Migration_Status;
MIG-002 | Parts not yet migrated | SELECT Part_ID, Part_Name FROM source_parts WHERE Migration_Status IN ('Pending','Failed');
MIG-003 | Pre vs Post migration count check | SELECT (SELECT COUNT(*) FROM source_parts) AS source_count, (SELECT COUNT(*) FROM target_parts) AS target_count;
QA-001 | Post-migration data integrity check | SELECT s.Part_ID FROM source_parts s LEFT JOIN target_parts t ON s.Part_ID = t.Part_ID WHERE t.Part_ID IS NULL AND s.Migration_Status = 'Completed';